## Slide 1: Project Management Financial management
Katrine Sandvad
Chiara Bearzotti
(Project Office at DMI)
Blue-Action Kick off 18-20 January 2017

## Slide 2: Amendment status
Replacing IC3 with ISGlobal
  Transfer of budget to new partner
  Amendment to be approved by EC on February 5
Inclusion of Climate-KIC
  Split between DTU-AQUA and Climate-KIC
  Amendment to be finalised
Inclusion of DNV Japan
  Split between DNV GL and DNV Japan
  Amendment to be finalised
Prefinancing to Climate-KIC, DNV Japan and ISGlobal is possible when the amendments have been approved by the EC
Notes: C

## Slide 3: Reports due: Who > to whom
Contents
Deliverables : Partner > Coordination (T) > EC
Milestones : Partner > Coordination (T) > EC
Progress reports: WP leader > Coordination (T) > EC
Communication activitites: Each scientist > WP8 and Project Office > EC
Dissemination activities : Each scientist > WP8 and Project Office > EC
Finances
6-month interim financial reports: partner > Project Office (T)
Financial reports: Each partner > Project Office > EC
(T)= template available in the intranet soon
Please pass this slide to your Blue-Action colleagues at home!
Notes: C

## Slide 4: Interim Financial Reports to DMI
Every six months to track progress in the project
In terms of:
budget allocated vs spent (plan vs actuals)
Person-months (plan vs actuals)
Positions field: how many human resources are allocated?
Who: each partner institution
When: on a six-month basis
Delivery to: DMI (Katrine and Chiara) with full details
Template: available in the intranet soon
Please pass this slide to your financial officer at home!
NEW
Notes: K

## Slide 5: Time table for financial reporting
Report | Period covered | Deadline
Interim Period 1 | 01/12/2016 - 31/05/2017 | 30-06-2017
Interim Period 2 | 01/06/2017 - 30/11/2017 | 01-01-2018
Reporting Period 1 | 01/12/2016 - 31/05/2018 | 30-06-2018
Interim Period 3 | 01/06/2018 - 30/11/2018 | 01-01-2019
Interim Period 4 | 01/12/2018 - 31/05/2019 | 30-06-2019
Reporting Period 2 | 01/06/2018 - 30/11/2019 | 01-01-2020
Interim Period 5 | 01/12/2019 - 31/05/2020 | 30-06-2020
Interim Period 6 | 01/06/2020 - 30/11/2020 | 01-01-2021
Reporting Period 3 | 01/12/2019 - 28/02/2021 | 31-03-2021
NEW
Notes: K

## Slide 6: Eligibility of costs
Personnel costs:
  Recruitment of new research staff compliant to Art. 32 GA requirements
  Reporting of costs – new rules November 2016: harmonisation at partner level
Subcontracting/outsourcing of activities: not foreseen
Other direct costs
  Travel
  Equipment
  Other services = ask the Project Office
In general:
Costs must be actual (i.e. registered in the accounts)
Costs must be documented (otherwise, they never incurred!)
Costs must be reported by each partner, at WP level
Please pass this slide to your financial officer at home!
NEW
Notes: K

## Slide 7: Dissemination activities database
Online database of the European Commission
Tracking of dissemination activity is mandatory (contractual requirement)
When: Continuously
Delivery to: Project Office
Please pass this slide to your Blue-Action colleagues at home!
Notes: C

## Slide 8: Type of activities + Audiences
Organisation of a Conference
Participation in a conference
Organisation of a workshop
Participation in a workshop
Participation in an event other than a conference or workshop
Participation in activities organised jointly with other H2020 project(s)
Video/film
Press release
Non-scientific and non-peer reviewed publications (popularised publications)
Exhibition
Flyers
Training
Social media
Communication campaign (e.g radio, TV)
Brokerage event
Pitch event
Trade fair
Scientific Community (higher education, Research)
Industry
Civil Society
General Public
Policy makers
Medias, Investors
Customers
Notes: C

## Slide 9: Acknowledging the EU contribution
A contractual obligation set by the Grant Agreement with the EC: Non compliance = reduction of the grant by the EC.
“The Blue-Action project has received funding from the European Union’s Horizon 2020 research and innovation programme under grant agreement No 727852“
+
Apply these to your PowerPoint presentations, Posters, Articles (scientific publications), Reports….
Please pass this slide to your Blue-Action colleagues at home!
Notes: C

## Slide 10: Open Access to data & publications
Open access to research data thereby becomes applicable by default in Horizon 2020
Partners make their research data findable, accessible, interoperable and reusable (FAIR), to ensure it is soundly managed
Principle "as open as possible, as closed as necessary“: encouraging sound data management as an essential part of research best practice
Data Management Plan (D in month 6) +Updates of the Plan with reports to EC in month 18,36, 48 and at project closure
Guidelines on FAIR Data Management in Horizon 2020
NEW
Please pass this slide to your Blue-Action colleagues at home!
Notes: C

## Slide 11: Internal communication
Regular news exchange between all scientists and the Project Office: keep regular contact!
Intranet for archiving/exchanging documentation
Website
Please pass this slide to your Blue-Action colleagues at home!
Notes: C

## Slide 12: Key messages
Inform the Project Office about your activities
Remember to acknowledge the EC contribution everywhere
Provide the Project Office with information on your dissemination activity (PowerPoints, Posters, Reports…)
Regular updates from Project Office will come via mail: read them carefully
Some amendments will be implemented in the next few months: make sure you have the final DoA in your hands
Please pass this slide to your Blue-Action colleagues at home!

## Slide 13
The Blue-Action project has received funding from the European Union’s Horizon 2020 research and innovation programme under grant agreement No 727852
Thank you and keep in touch!