## Slide 1
Goal
To identify the current limitations in predicting Arctic climate (and its link to NH climate) and
to develop improved models and methodologies to enhance the skill of initialized climate predictions in the Arctic and over the NH.
An updated forecast ensemble will be performed with the improved systems and delivered to selected impact case studies.
WP4: Enhancing the capacity of seasonal-to-decadal predictions in the Arctic and over the Northern Hemisphere
Daniela Matei (MPI) and Noel Keenlyside (UiB)

## Slide 2
Task 4.1: Mechanistic and statistical skill assessment of baseline predictions
Month
1
12
24
36
48
Deliver initial data to WP5 from existing experiments from MPI, NorCPM, IPSL models [D4.1, month 6, Daniela/MPI]
Identify selected events for performing prediction case studies
Investigate approaches to extract most information from existing systems
Milestone 6 expected around month 12 to conclude discussion on these cases
D4.2 Report describing the benchmark performance of state-of-the-art prediction systems [month 24, Daniela/MPI]

## Slide 3
Task 4.1: Mechanistic and statistical skill assessment of baseline predictions
Month
1
12
24
36
48
Task 4.2: Coordinated experiments to quantify the contribution of the Artic and high latitude North Atlantic in predictability of Northern Hemisphere extreme weather and climate
Idealised prediction experiments with data added or withheld
2) Greenland Ice Sheet melt prediction experiments
Skill will be assessed in terms of the representation of mechanisms
Experiment protocol to be finalised around month 12 [MS 7]
D4.3: Report summarising the impact of the Arctic and high-latitude North Atlantic, and Greenland ice sheet melt on predictability of the Arctic, North Atlantic, and climate of surrounding continents [month 36, DMI, Torben]

## Slide 4
Task 4.1: Mechanistic and statistical skill assessment of baseline predictions
Month
1
12
24
36
48
1) Higher ocean and atmospheric resolution
2) Consistent initialisation of sea ice
3) Methods to reduce initial shock on predictions
Skill will be assessed in terms of the representation of mechanisms
Experiment protocol to be finalised around month 12 [MS 7]
D4.4: Datasets from all sensitivity prediction experiments available in standard data format, and fully documented to Blue Action modelling partners and impact case studies [month 36, UiB, Noel]
Task 4.3: Explore alternative ways of enhancing predictive skill through improved model configurations and innovative initialization techniques

## Slide 5
Task 4.1: Mechanistic and statistical skill assessment of baseline predictions
Month
1
12
24
36
48
Task 4.2: Identify predictability mechanisms
Task 4.3: Assessing improved systems
Task 4.3: Explore alternative ways of enhancing predictive skill
through improved model configurations and innovative initialization techniques
Only briefly discussed as starts month 24
D4.5: Report on the best practices for enhancing seasonal-to-decadal prediction skill in the Arctic with user- relevant linkages over the NH continents [month 48, NLeSC, Wilco]

## Slide 6: Other issues
Is there any infrastructure in the project for data sharing?
Collaboration with the following projects was identified.
  EU APPLICATE
  NordForsk ARCPATH
  EU INTAROS
  JPI INTERDEC
  BMBF MIKLIP
  BMBF RACE